RASMI LOGISTIC SERVICE

Event Management Report

HoA DRIVE Project

Solar Fridge Handover Ceremonies

| Client | Project Implementation Unit (PIU), DRIVE Project, Ministry of Finance, Federal Government of Somalia |
| --- | --- |
| Project | De-risking, Inclusion and Value Enhancement of Pastoral Economies in the Horn of Africa (HoA DRIVE) |
| Contract reference | [Contract No.] dated [date] |
| Event period | 18 August 2026 to 30 September 2026 |
| Locations | 9 districts across Galmudug, Banadir, South West, Hirshabelle and Jubaland |
| Beneficiaries | 540 families (60 per district) |
| Project focal point | Abdulkadir Hussein Hassan |
| Submitted by | Rasmi Logistic Service, Waabari Mall, Mogadishu |
| Date of report | 14 October 2026 |

# 1. Background

The HoA DRIVE Project is implemented by the Project Implementation Unit (PIU) of the Ministry of Finance, Federal Government of Somalia, with financing from the World Bank. Under the project, solar-powered fridges are provided to women milk vendors so they can keep milk fresh, reduce spoilage and increase income from milk sales.

Public handover ceremonies were organised in each target district to formally hand over the fridges to beneficiary families and to create a visible record of the support provided.

Rasmi Logistic Service was contracted by the PIU under Contract No. [Contract No.] dated [date] to provide logistics support for these handover ceremonies. This report summarises the services delivered under the contract.

# 2. Executive Summary

Between 18 August and 30 September 2026, Rasmi Logistic Service supported fridge handover ceremonies in nine districts across four Federal Member States and Banadir. A total of 540 families received their fridges (60 per district).

| Districts | Families | FMS + Banadir | Period |
| --- | --- | --- | --- |
| 9 | 540 | 4 + 1 | 18 Aug 2026 to 30 Sep 2026 |

Services delivered, in line with the contract:

- Carrying and handling of fridge equipment in all nine districts.

- Catering in Afgoye and Balcad only.

- Vehicle rent and transportation, within city or intercity, in all nine districts.

- Media coverage of the ceremonies in all nine districts.

Reach by Federal Member State:

| FMS / Area | Districts | Date(s) | Families |
| --- | --- | --- | --- |
| Galmudug | Dhusamareeb, Cadaado, Galkacyo | 18 Aug 2026 | 180 |
| Banadir | Mogadishu | 6 Sep 2026 | 60 |
| South West | Afgoye | [date] | 60 |
| Hirshabelle | Jowhar, Beledweyne, Balcad | 14 Sep 2026 | 180 |
| Jubaland | Kismayo | 30 Sep 2026 | 60 |
| Total | 9 districts |  | 540 |

# 3. Scope of Services

The table below sets out the services under the contract and where each was provided. The fridges were supplied by the project; Rasmi's role was logistics support for the handover.

| Service | Description | Coverage |
| --- | --- | --- |
| Fridge carrying and handling | Loading, moving and carrying the fridge equipment to the venue and helping each family carry their fridge after handover. | All 9 districts |
| Catering | Refreshments for participants and guests at the ceremony. | Afgoye and Balcad only |
| Vehicle rent / transportation | Vehicle rent for movement within the city, and intercity transport between locations where required, for the team, materials and fridges. | All 9 districts |
| Media coverage | Photography and video coverage of each ceremony. All media is available through the link in Section 6. | All 9 districts |

# 4. Delivery by District

| # | District | FMS / Area | Date | Families | Fridge carrying | Catering | Transport | Media |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dhusamareeb | Galmudug | 18 Aug 2026 | 60 | Yes | No | Yes | Yes |
| 2 | Cadaado | Galmudug | 18 Aug 2026 | 60 | Yes | No | Yes | Yes |
| 3 | Galkacyo | Galmudug | 18 Aug 2026 | 60 | Yes | No | Yes | Yes |
| 4 | Mogadishu | Banadir | 6 Sep 2026 | 60 | Yes | No | Yes | Yes |
| 5 | Afgoye | South West | [date] | 60 | Yes | Yes | Yes | Yes |
| 6 | Jowhar | Hirshabelle | 14 Sep 2026 | 60 | Yes | No | Yes | Yes |
| 7 | Beledweyne | Hirshabelle | 14 Sep 2026 | 60 | Yes | No | Yes | Yes |
| 8 | Balcad | Hirshabelle | 14 Sep 2026 | 60 | Yes | Yes | Yes | Yes |
| 9 | Kismayo | Jubaland | 30 Sep 2026 | 60 | Yes | No | Yes | Yes |
|  | Total |  |  | 540 | 9 | 2 | 9 | 9 |

# 5. Logistics and Coordination

Each district was planned and run as a separate deployment, with the same service standard applied at every site.

## 5.1 Transportation

- Within city: vehicle rent to move the team, materials and fridges between storage and the ceremony venue.

- Intercity: transport between districts where the ceremony site required travel from another city [Rasmi to list the districts served by intercity transport].

## 5.2 Catering

Catering was provided in Afgoye and Balcad only, as set out in the contract. No catering was provided in the other seven districts.

## 5.3 Ceremony steps

- Prepare: confirm the district plan, date, venue and transport with the PIU focal point.

- Mobilise: move the team and fridge equipment to the district and set up the venue.

- Hand over: fridges handed over to the 60 beneficiary families; handover list signed.

- Carry: team helps each family carry their fridge from the venue.

- Record: photo and video coverage of the ceremony.

- Close: wrap up on site and confirm the outcome with the PIU focal point.

## 5.4 Coordination with the PIU

Rasmi kept regular contact with the project focal point, Abdulkadir Hussein Hassan, before and during each ceremony to confirm dates, venues and arrangements.

# 6. Media Coverage

Photo and video coverage was provided at all nine ceremonies. The full media files are available at:

| District | Media link / folder |
| --- | --- |
| Dhusamareeb | [link] |
| Cadaado | [link] |
| Galkacyo | [link] |
| Mogadishu | [link] |
| Afgoye | [link] |
| Jowhar | [link] |
| Beledweyne | [link] |
| Balcad | [link] |
| Kismayo | [link] |

# 7. Challenges and How They Were Managed

| Challenge | How it was managed |
| --- | --- |
| Distance between districts | Planned transport per district (within city or intercity) and scheduled travel so the team arrived in time to set up. |
| Security and access | Coordinated movements with the project team and local authorities, and kept travel and set-up within safe working hours. |
| Carrying fridges | Team helped each family carry their fridge so the equipment reached them safely. |
| Consistent quality across 9 sites | Used the same service checklist in every district. |

# 8. Lessons Learned and Recommendations

## What worked well

- A standard service checklist for every district.

- Planning each ceremony as its own deployment.

- Helping families carry their fridges on the day.

## For future handovers

- Agree the district schedule with the PIU early.

- Confirm venue, transport type and any catering per district in advance.

- Share media coverage with the PIU within a set number of days after each ceremony.

# 9. Conclusion

Rasmi Logistic Service supported nine handover ceremonies in which 540 families received solar fridges. Each ceremony is a practical step towards safer milk storage, less spoilage and stronger incomes for families who depend on milk sales.

We thank the Project Implementation Unit, Ministry of Finance, and the project focal point, Abdulkadir Hussein Hassan, for their support throughout.

| Prepared by | Verified by |
| --- | --- |
| Mohamed Jama Osman Operation Manager, Rasmi Logistic Service | Abdulkadir Hussein Hassan Project Focal Point, HoA DRIVE Project |
| Signature: ____________________ | Signature: ____________________ |
| Date: ____________________ | Date: ____________________ |

# Annexes

- Annex A: Signed handover / acknowledgement lists per district

- Annex B: Selected photos per district

- Annex C: Media coverage link(s)