EVENT MANAGEMENT REPORT

HoA DRIVE Project

Solar Fridge Handover Ceremonies

Hirshabelle — State Report

“Delivering Cold-Chain Livelihoods”

SUBMITTED TO Abdulkadir Hussein Hassan Focal Point, HoA DRIVE Project Project Implementation Unit (PIU), Ministry of Finance, Federal Government of Somalia

| Client | Project Implementation Unit (PIU), DRIVE Project, Ministry of Finance, Federal Government of Somalia |
| --- | --- |
| Project | De-risking, Inclusion and Value Enhancement of Pastoral Economies in the Horn of Africa (HoA DRIVE) |
| Contract reference | [Contract No.] dated [date] |
| Area covered | Hirshabelle: 3 districts (Jowhar, Beledweyne and Balcad) |
| Ceremony date | 14 September 2026 |
| Beneficiaries | 200 families |
| Project focal point | Abdulkadir Hussein Hassan |
| Submitted by | Rasmi Logistic Service, Waabari Mall, Mogadishu |
| Date of report | 14 October 2026 |

# 1. Background

The HoA DRIVE Project is implemented by the Project Implementation Unit (PIU) of the Ministry of Finance, Federal Government of Somalia, with financing from the World Bank. Under the project, solar-powered fridges are provided to women milk vendors so they can keep milk fresh, reduce spoilage and increase income from milk sales.

Public handover ceremonies were organised in each target district. This report covers the ceremonies in Hirshabelle: Jowhar, Beledweyne and Balcad. Rasmi Logistic Service was contracted by the PIU to provide logistics support for these ceremonies, and the fridges were supplied by the project.

# 2. Summary

In Hirshabelle, Rasmi Logistic Service supported fridge handover ceremonies in 3 districts on 14 September 2026. A total of 200 families received their fridges.

| Districts | Families | Region | Date |
| --- | --- | --- | --- |
| 3 | 200 | Hirshabelle | 14 Sep 2026 |

Services delivered in Hirshabelle:

Carrying and handling of fridge equipment in all 3 districts.

Vehicle rent and transportation, within the city and intercity, in all 3 districts.

Media coverage of the ceremony in all 3 districts.

Catering in Balcad only.

# 3. Scope of Services

The table sets out the services under the contract and where each was provided in this area. The fridges were supplied by the project; Rasmi’s role was logistics support for the handover.

| Service | Description | Coverage |
| --- | --- | --- |
| Fridge carrying and handling | Loading, moving and carrying the fridge equipment to the venue and helping each family carry their fridge after handover. | All 3 districts |
| Catering | Refreshments for participants and guests at the ceremony. | Balcad only |
| Vehicle rent / transportation | Vehicle rent for movement within the city, and intercity transport where required, for the team, materials and fridges. | All 3 districts |
| Media coverage | Photography and video coverage of the ceremony. Links and details are in Annex A. | All 3 districts |

# 4. Delivery by District

| # | District | Date | Families | Fridge carrying | Catering | Transport | Media |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Jowhar | 14 Sep 2026 | 80 | Yes | – | Yes | Yes |
| 2 | Beledweyne | 14 Sep 2026 | 60 | Yes | – | Yes | Yes |
| 3 | Balcad | 14 Sep 2026 | 60 | Yes | Yes | Yes | Yes |
|  | Total |  | 200 | 3 | 1 | 3 | 3 |

# 5. Logistics and Coordination

Each district in Hirshabelle was planned and run as a separate deployment, with the same service standard applied at every site.

## 5.1 Transportation

Within city: vehicle rent to move the team, materials and fridges between storage and the ceremony venue.

Intercity: transport between locations where the ceremony site required travel from another city:

Mogadishu – Balcad – Mogadishu

## 5.2 Catering

Catering was provided in Balcad, as set out in the contract.

## 5.3 Ceremony steps

Prepare: confirm the district plan, date, venue and transport with the PIU focal point.

Mobilise: move the team and fridge equipment to the district and set up the venue.

Hand over: fridges handed over to the 200 beneficiary families in Hirshabelle; handover list signed.

Carry: team helps each family carry their fridge from the venue.

Record: photo and video coverage of the ceremony.

Close: wrap up on site and confirm the outcome with the PIU focal point.

## 5.4 Coordination with the PIU

Rasmi kept regular contact with the project focal point, Abdulkadir Hussein Hassan, before and during each ceremony to confirm dates, venues and arrangements.

# 6. Media Coverage

Photo and video coverage was provided at all 3 ceremonies in Hirshabelle. Links and details for each district are in Annex A.

# 7. Challenges and How They Were Managed

| Challenge | How it was managed |
| --- | --- |
| Distance and travel | Planned transport per district and scheduled travel so the team arrived in time to set up. |
| Security and access | Coordinated movements with the project team and local authorities, and kept travel and set-up within safe working hours. |
| Carrying fridges | Team helped each family carry their fridge so the equipment reached them safely. |
| Consistent quality | Used the same service checklist in every district. |

# 8. Conclusion

Rasmi Logistic Service supported the handover ceremonies in Hirshabelle, in which 200 families received solar fridges. Each ceremony is a practical step towards safer milk storage, less spoilage and stronger incomes for families who depend on milk sales.

We thank the Project Implementation Unit, Ministry of Finance, and the project focal point, Abdulkadir Hussein Hassan, for their support throughout.

| Prepared by | Verified by |
| --- | --- |
| Mohamed Jama Osman Operation Manager, Rasmi Logistic Service | Abdulkadir Hussein Hassan Project Focal Point, HoA DRIVE Project |
| Signature: | Signature: ____________________ |
| Date: 14 October 2026 | Date: ____________________ |

# Annex A: Media Coverage — Links and Details

Photo and video coverage was provided at all 3 ceremonies in Hirshabelle. The details and links for each district are below.

## A.1  Jowhar

| District | Jowhar |
| --- | --- |
| Region | Hirshabelle |
| Ceremony date | 14 September 2026 |
| Families | 80 |
| Media provided | Photography and video coverage of the ceremony |
| Photos and videos | https://www.facebook.com/reel/1881138039767781 |

## A.2  Beledweyne

| District | Beledweyne |
| --- | --- |
| Region | Hirshabelle |
| Ceremony date | 14 September 2026 |
| Families | 60 |
| Media provided | Photography and video coverage of the ceremony |
| Photos and videos | [link] |

## A.3  Balcad

| District | Balcad |
| --- | --- |
| Region | Hirshabelle |
| Ceremony date | 14 September 2026 |
| Families | 60 |
| Media provided | Photography and video coverage of the ceremony |
| Photos and videos | https://www.facebook.com/reel/4439016306360579 |